## Sheet1
Estimate -Price Proposal Page
PHASE 1
Deliverable | Short Description/Summary | Estimated Completion | Estimated Cost
Deliverable 1 | PSTN vs. VoIP Executive Briefing document and PowerPoint presentation. Summary: Develop an Executive Briefing that compares, in non-technical terms, the pros, cons, and considerations of operating a combined voice and data network (VoIP) vs. separate PSTN Voice and data networks | Estimated time to complete: 3 – 5 business days
Deliverable 2 | Executive Summary of key telecommunications capabilities to meet the Judiciary’s needs over the next 5 years. Key findings PowerPoint presentation. Summary: 2. Meet with up to 7 key operational and technology managers and document the critical and desired telecommunications features and capabilities to meet their operational and customer service future vision. | Estimated time to complete: 5 – 7 business days
Deliverable 3 | Executive Summary document highlighting major weaknesses and issues with the current environment in terms of addressing the capabilities contained in Deliverable 2. Supporting PowerPoint presentation. Summary: This review should include, but not be limited to internal direct dialing throughout the Judiciary, long distance dialing, voicemail, system / PBX administration, and business continuity. | Estimated time to complete: 5 – 10 business days
PHASE 2
Deliverable | Short Description/Summary | Estimated Completion | Estimated Cost
Deliverable 4 | Alternative Analysis of VoIP approaches with preliminary recommendation and cost considerations. Summary: The Analysis must consider the functional requirements gathered in Phase 1, phased implementation alternatives, technical considerations, and preliminary cost considerations. This will involve gaining an understanding of the Judiciary’s data network, network management capabilities for adequacy to effectively deliver and manage consistent voice services as well as managed external services approaches. | Estimated time to complete: 10 – 20 business days
PHASE 3
Deliverable | Short Description/Summary | Estimated Completion | Estimated Cost
Deliverable 5 | AOC Tactical plan with estimated resources needed and time frames with supporting PowerPoint presentation. Summary: Develop a sequenced plan (roadmap) to implement VoIP services to satisfy the immediate needs of the planned AOC facility initiatives while maintaining continuity with the remaining PSTN statewide network. | Estimated time to complete – 5 – 10 business days
Deliverable 6 | Strategic Implementation Plan with supporting PowerPoint presentation. Summary: Building on the AOC Tactical Plan, develop an implementation roadmap to adopt advanced VoIP functionality required by AOC but beyond the scope of the Tactical Plan, and a framework for expansion of VoIP statewide. | Estimated time to complete – 10 – 20 business days
Total Cost Phase 1, 2 and 3 (Deliverables 1-6) |  |  | 0
OPTIONAL - PHASE 4
Deliverable | Short Description/Summary | Estimated Completion | Cost
Deliverable 7 (Optional) | RFP(s): The RFP(s) will follow the approved format for the AOC. Assistance may be requested to develop the Statement of Work, deliverables, and timeframes. | Estimated time to complete: 10 – 20 business days
Deliverable 8 (Optional) | Proposal Evaluation – Expertise may be requested during the selection and award process of proposals received from deliverable 7. Summary: Evaluation ratings and supporting notes | Estimated time to complete: 5 – 10 business days
Total Cost Phase 3 Optional (Deliverables 7 and 8) |  |  | 0